## Sheet1
TEAM LEADER : ABHISHEK RAJ
FRONTEND TEAM Lead - Abhishek Raj
Date | Team Leader :- Abhishek Raj
Team Member Name |  |  | Abhishek Raj | Aishwarya Tengli |  |  | Amrata Patel |  | Adarsh Gangurde | Amar Lohar | Akhil Vailala
Date | Day |  | Activities | Activities |  |  | Activities |  | Activities | Activities | Activities
2022-03-22 | 1 |  | Admin Login | Payment Page |  |  | Admin Products Page |  | Admin Home Page | Customer Cart Page | Customer Login Page
2022-03-23 | 2 |  | Admin Login services | Payment Page Services |  |  | Admin Products Page Services |  | Admin Home Services | Customer Cart Services | Customer Login Page Services
2022-03-24 | 3 |  | Admin View Customer | Payment Page Services |  |  | Category Page |  | About Page | Customer Product Page | Customer Registeration Page
2022-03-25 | 4 |  | Services File | Payment Page Services |  |  | Category Page Services |  | Admin Product Page | Customer Page Service Page | Customer Registeration Page Services
2022-03-26 | 5 |  | All Main TS File | Payment Succes Page |  |  | Customer Dashboard |  | Admin Product Page | Customer Profile Update | Home Page
2022-03-27 | 6 |  | Mobile View | Payment Succes Page |  |  | Customer Dashboard Services |  | Admin Edit Product | Customer Profile Update Services | Home Page Services
2022-03-28 | 7 |  | Integration | Integration |  |  | Integration |  | Integration | Integration | Integration
2022-03-29 | 8 |  | Integration | Integration |  |  | Integration |  | Integration | Integration | Integration and Api Testing
BACKEND TEAM Lead - Afzal Hussain
Date
Team Member Name |  |  | Afzal Hussain |  | Akshay Agrawal |  |  | Ajinkya Dimothe | Akshay Ak
Date | Day |  | Activities |  | Activities |  |  | Activities | Activities
2022-03-22 | 1 |  | Admin Login Backend |  | Product Backend |  |  | Cart Backend | Product Backend
2022-03-23 | 2 |  | Customer Login Backend |  | Product Backend |  |  | Cart Backend | Product Backend
2022-03-24 | 3 |  | Login Controller |  | Product Controller |  |  | Cart Controller | Product Conroller
2022-03-25 | 4 |  | Login Dao |  | ProductDao |  |  | CartDao | ProductDao
2022-03-26 | 5 |  | LoginDaompl&Login Dto |  | ProductDaompl |  |  | CartDaompl | ProductDaompl
2022-03-27 | 6 |  | Functionalities Checking |  | Functionality Checking |  |  | Functionality Checking | Integration and solving errors
2022-03-28 | 7 |  | Integration |  | Integration |  |  | Integration | Integration and solving errors
2022-03-29 | 8 |  | Integration |  | Api Testing Using Postman |  |  | Integration | Documentation